|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task Name | Duration | Work | Start | Finish | Predecessors | Resource Names |
| **WP1 – New Ericsson probe into IN network environment** | **64 days** | **33 days** | **Mon 17/10/11** | **Thu 12/01/12** |  |  |
| Design | 1 day | 1 day | Mon 17/10/11 | Mon 17/10/11 |  | **Alex Silva** |
| Install new Ericsson probe into environment | 1 day | 1 day | Tue 18/10/11 | Tue 18/10/11 | 5 | **Alex Silva** |
| Create probe rules | 4 days | 2 days | Wed 19/10/11 | Mon 24/10/11 | 6 | Chris Janes[50%] |
| Run probe to receive/collect events | 4 days | 2 days | Tue 25/10/11 | Fri 28/10/11 | 7 | Chris Janes[50%] |
| Create/modify policies | 40 days | 20 days | Mon 31/10/11 | Fri 23/12/11 | 8 | Chris Janes[50%] |
| Test that events and policies produce same results as in previous system. | 10 days | 5 days | Mon 26/12/11 | Fri 06/01/12 | 9 | Chris Janes[50%] |
| Document and handover to support | 2 days | 1 day | Mon 09/01/12 | Tue 10/01/12 | 10 | Chris Janes[50%] |
| Deploy | 2 days | 1 day | Wed 11/01/12 | Thu 12/01/12 | 11 | Chris Janes[50%] |