## Sheet1
Mobilink Probe Installation sequence
Network | EMS | Probe | Vendor OS Platform | OS - Probe compatibility | Comment | Order of Install | Tentative date
BSS | Huawei BSC6000V900R008C01B051Sp18 | nco_p_huawei_m2000_corba | Solaris | Yes | Mobilink to confirm if install can be carried out on vendor server | 4 | 2010-03-25 | send e-mail back to huawei regarding probe installation | install on ibm sever and request IOR file, corba bus details etc. - check compatibility with AIX
| Motorola GSR 8 | nco_p_motorola_3gpp_omcr_gsm9 | Solaris | Yes | test on one if compatibile, continue with other. Currently GSR 8 | 5 | 2010-03-25
| ALU B-9 | nco_p_alcatel_omcr1353ra_b10 | Solaris | Yes | test on one if compatibile, continue with other. Currently B-9 | 6 | 2010-03-26 | requires Sun Solstice CMIP 9.0 patch - check aix compatibility.
TXN | Huawei T2000 | nco_p_huawei_T2000_corba | Solaris and Windows. | Windows platform not supported |  | 3 | 2010-03-24 | probe installed, needs config for corba server, Huawei to provide details | aix probe, second instace for windows machine. | 1 | 2. check huawei windows server probe. | solaris server- 10.231.101.100 root rootkit
| NEC PNMS | nco_p_mttrapd | N/A |  | mibs to be provided by Mobilink | 1 | 2010-03-24 | installed primary and failover, configured NCKL, mibs need configuration
| Tellabs 8100 | nco_p_tellabs_8000 | Windows (install on server) | Windows platform not supported | Check windows probe compatibility | 2 | 2010-03-24 | installed, configured and running in failover - vendot to send alerts | mobilink to implement changes
Core | Siemens - Switch Commanderv11 | nco_p_siemens_sc_scr12 | Solaris | Yes |  | 9 | 2010-03-30
| Huawei | nco_p_huawei_m2000_corba | Solaris | Yes | NBI availability needs to be checked with vendor | 10 | 2010-03-31
| STP NetBOSS V4.4 | nco_p_eaglestp | Not Available | Windows platform not supported | installation at a later stage in phase one - upgrade in May | 12
| NSN MSS R4 | nco_p_nokia_netact_3gpp | Solaris | Yes | NBI availability needs to be checked with vendor | 11 |  | check nec alarm rate for next two hours.
IN/VAS | IN @COM 7.9,8.5 | nco_p_mttrapd | N/A | Yes | mobilink to check trapexploder config with vendors. Mibs required | 7 | 2010-03-29 | send ip address of where the probe wil be installed on server
| SMSC LogicaCMG 5.0 , 5.1 | nco_p_mttrapd | N/A | Yes | nodes sending alarms directly | 8 | 2010-03-29
ITM | IBM Tivoli Monitor Alarm handling | nco_p_eif_itm | N/A | Yes | Probe for IBM Tivoli Monitor Alarm handling | 13