## Sheet1
Policy | Observation/Defect | Priority | Owner | Commentary | Status (Open, In Progress, Closed)
ML_IP_Bulk_Alarm | Incident records not being raised |  | Chris | This is because Synthetic events generated by this policy are not being processed by ML_RaiseTT_FirstOccurrence . It is a simple Change to update this trigger. I have requested permission to make this change from ML | In Progress
ML_IP_Bulk_Alarm | Not all Events are having the correct EventID set by the rules associated to this policy |  | Chris | ML to provide examples of this. | Open