## VERSION CONTROL
Version | Date | Change Description | Who
V1
V2
V3
V4
V5
V6
V7
V8
V9
V10
V11
V12
V13
V14
V15
V16
V17
V18
V19
V20
V21
V22
V23
V24
V25
V26
V27
V28
V29
V30
V31
V32
V33
V34
V35
V36
V37
V38
V39
V40
V41
V42
V43
V44
V45
V46
V47
V48

## Risk, Issue, Defect, Action
Reference | ServiceNow Support Ref | Customer/IBM Risk, Issue, Defect ref | Related System/ Module | Date Raised | Raised by | Risk log | Action, Defect, Issue, Key Decision, Risk | Description | Category | Owner/Resolving Organisation | Owner/Resolving Name | Priority {Critical, High, Medium, Low} | Status {Open, Closed} | Impact {High, Medium, Low} | Probability {High, Medium, Low} | Difficulty to Control | Impact/Reason | Potential Impact | Update / Actions | Target Resolution Date | Target Resolution Date | Target Resolution Date | Attached File
001 |  | Risk | VAS Domain/Impact | 2011-07-18 | Nitesh |  | Issue | Requested the alarm mapping details for remaining VAS entities. Also send the current mapping which I have to verify (in case of any changes) | Build | Mobilink | Saad Saeed Khan | High | Closed | High | High | Medium |  | Respective alarms will not process correclty if incomplete/incorrect mapping is provided |  |  | No
002 |  |  |  | 2011-07-22 | Nitiesh |  | Issue | GPU_CONN Table data urgently required | Build | Mobilink |  | High | Closed
003 |  | Issue | WiMax | 2011-07-21 | Alex |  | Issue | Mobilink Response Required | Build | Mobilink |  | High | Closed | [7 empty] | No
004 |  |  |  |  | Alex |  |  | WiMax Connectivity Table awaited from ML |  |  |  | High | Closed
005 |  | Issue | WiMAx | 2011-07-21 | Alex |  | Issue | Huawei T2000 Table With Node/Site Code, Port slot for related Wimax entires required | Build | Mobilink |  | High | Closed | [7 empty] | No
006 |  | Issue | WiMax | 2011-07-21 | Alex |  | Issue | MSD LLD Awaiting Ml Approval | Build | Mobilink |  | High | Closed | [7 empty] | No
007 |  |  |  |  | Alex |  | Issue | Alcatel Communications failure LLD approval awaited | Build | Mobilink |  | High | Closed
008 |  | Risk | IP | 2011-06-20 | Mansoor |  | Risk | Huawei Devices Configuration awaited from ML for Non-MPLS devices | Build | Mobilink |  | High | Closed | [7 empty] | No
009 |  | Risk | IP | 2011-06-20 | Mansoor |  | Risk | MPLS devices config info awaited. Two test devices provided & discovered | Build | Mobilink |  | High | Closed | [7 empty] | No
010 |  | Risk | IP | 2011-06-20 | Mansoor |  | Risk | Proxy credentials required for downloading Fix Pack and DLA adaptors for patching TADDM application | Build | Mobilink |  | High | Closed | [7 empty] | No
011 |  | Issue | MIBS/Probes | 2011-07-01 | Mihai |  | Issue | OMG/MMSC Events , Traps awaited from Vendor | Build | Mobilink |  | High | Closed | [7 empty] | No
012 |  | Issue | MIBS/Probes | 2011-07-01 | Mihai |  | Issue | I2000 CRBT, EVC, ICS Rules configured, ML to confirm acceptance | Build | Mobilink |  | High | Closed | [7 empty] | No
013 |  | Issue | MIBS/Probes | 2011-07-01 | Mihai |  | Issue | BT/Gcash/ADM awaiting traps & Mapping confirmation from ML | Build | Mobilink |  | High | Closed | [7 empty] | No
014 |  | Risk | IMPACT | 2011-07-18 | Alex |  | Action | Sign Off Awaited from ML for Dragon Wave Rules Files | Build | Mobilink |  | High | Closed | [7 empty] | No
015 |  | Risk | TSRM Gateway | 2011-07-18 | Alex |  | Action | Sign Off Awaited from ML for Alcatel Rules Files | Build | Mobilink |  | High | Closed | [7 empty] | No
016 |  | Risk | Impact | 2011-07-18 | Alex |  | Action | Sign Off Awaited for Huawei Service Imapcting Alarm Policies | Build | Mobilink |  | High | Closed | [7 empty] | No
017 |  | Risk | Impact | 2011-07-18 | Julian |  | Risk | Memory leak | Support | IBM |  | High | Closed | [7 empty] | No
018 |  | Risk | IP | 2011-06-20 | Mansoor |  | Risk | MPLS/Non MPLS devices availability from ML causing over 20+ days delay | Build | Mobilink |  | High | Closed
019 |  | Risk | MIBS/Probes | 2011-07-25 | Mihai |  | Risk | Awaiting VMS Traps & Mapping Information | Build | Mobilink |  | High | Closed
020 |  | Issue | MIBS/Probes | 2011-07-25 | Mihai |  | Risk | ML to acquire severity mappings from Acision for OMG traps | Build | Mobilink |  | High | Closed
021 |  | Issue | MIBS/Probes | 2011-07-25 | Mihai |  | Risks | MMSC Traps still awaited from Vendor | Build | Mobilink |  | High | Closed
022 |  | Issue | IMPACT IP_to_CORE Policy | 2011-09-14 | Sohaib |  | Issue/Defect | 3 issues: 1 bug, 2 situations where behaviour is as expected, awaiting Sohaib's feedback. 1) SYN_IP_MPLS_002 were created for events with Z Node not in ITNM tbl – fixed, under observation 2) SEs are created and NEs are flagged as child events only for A->Z direction (not Z->A as well). Waiting for Sohaib feedback if both directions need to be covered by same SE. 3) @RemoteInterface population – Fixed | Build | Innovise | Mihai | High | Open | Medium |  |  |  |  | 1st fixed, provided explanations for the other 2 (behaviour as expected), awaiting Sohaib's feedback 16 Sep - 3rd Point resolved, addressed by blanket CR for all IP policies 16 Sep - Point 2 to be addressed by CR 19 Sep - To be addressed by CR, however ML checking to see if required info is avaialble from MPLS topology. If that exists the CR would no longer be required, may need a table change 21 Sep - Awaiting clarification re requirement for CR, else policy functioning correctly
023 |  | Issue | IMPACT IP_to_TxN Policy | 2011-09-14 | Sohaib |  | Issue/Defect | alarms in scope are not currently picked up by the policy 16 Sep - Probe Rules fixed 16 Sep - Policy being adressed | Build | Innovise | Mihai for Probe, Alex for Policy | High | Open | Medium |  |  |  |  | Resolution in progress - Need to fix rules condition to properly set @ParentChild field as needed by policy filter 19 Sep - Probe Rule fixed confirmed OK 19 Sep - Policy ammended by 'blanket CR' released for UAT 21 Sep - ML confirmed that grouping of Alarams for SE is not quite right in some cases, particularly for those connected to the same remote interface, AS to investigate
024 |  | Issue | IMPACT ML_IP_Bulk_Alarm | 2011-09-14 | Sohaib |  | Issue/Defect | Incident records not being raised | Build | Innovise | Chris | High | Closed | Medium |  |  |  |  | In Progress - This is because Synthetic events generated by this policy are not being processed by ML_RaiseTT_FirstOccurrence . It is a simple Change to update this trigger. I have requested permission to make this change from ML 16 Sep - Resolved under observation
025 |  | Issue | IMPACT ML_IP_Bulk_Alarm | 2011-09-14 | Sohaib |  | Issue/Defect | Not all Events are having the correct EventID set by the rules associated to this policy | Build | Innovise | Chris | High | Closed | Medium |  |  |  |  | ML to provide examples of this. 16 Sep - Resolved Under Observation
026 |  | Issue | IMPACT - Re all IP Policies | 2011-09-14 | Julian |  | Issue | Possible that ITNM generated events do not capture all scnearios 16 Sep - Ken helping with ITNM, missing device on 10.215. now discovered | Build | Innovise/Mobilink | Julian | High | Open | Medium |  |  |  |  | 19 Sep - ITNM Generated events not visible, may have to have some network events being plugged in 21 Sep - JL to get update from Ken re his current status, observations on this
027 |  | Issue | IMPACT IP-BSS (NON-MPLS) | 2011-09-14 | Julian |  | Issue | ifAlias does not contain required data for NON_MPLS sources | Build | Innovise/Mobilink | Julian | High | Open | Medium |  |  |  |  | Agreed with Sohaib that this will be handled within IP-BSS policy itself va lookup to ITNM database 16 Sep - CR impacting the 3 policies, CR created and approved, change applied to the IP to BSS policy 19 sep - Change in UAT for all three BSS, CORE & TXN IP policies 21 Sep - Awaiting confirmation from ML re system behaviour
028 |  | Issue | IMPACT - IP-BSS (WIMAX) | 2011-09-14 | Julian |  | Issue | ITNM connectectivity data is not hierarchical | Build | Innovise/Mobilink | Julian | High | Open | Medium |  |  |  |  | ML to supply WIMAX data as spreadsheet to allow policy development 16 Sep - A script will have to be developed to take data from ITNM & load it. Lower priority as presently the off line table can be used 19 Sep - Topology table data loaded from spreadsheet to start UAT (data fairly static). Script will next be developed to transform ITNM data into topological format. IP-BSS WMX policy likely in UAT on Wed 21st 21 Sep - ML to provide updated WMX data with interface details today, this can be used for the outstanding downstream interface issue for IP-BSS WMX policy. code to process this to be developed
029 |  | Issue | IMPACT - Alcatel PSD/SD | 2011-09-14 | Talal |  | Defect | duplicate SE | Build | Innovise | Alex | High | Closed | Medium |  |  |  |  | In progress - I've done few modification in the code in order to fix this and is now under observation. 16 Sep - Fix in place, under observation
030 |  | Issue | Alcatel PSD/SD | 2011-09-14 | Talal |  | Defect | Clearence missing for some events | Build | Innovise | Alex | High | Closed | Medium |  |  |  |  | In Progress - Found that few clear missing caused by duplicate SE issue and I believed is fixed now. It's under ML observation. 16 Sep - Fix in place under observation
031 |  | Issue | VAS Domain/Impact | 2011-09-16 | David P |  | Issue | There appears to be a need to use IP address for the enrichment lookup for the VAS domain too as the alarm doesn't seem to have any sensible value for node or node alias. Also the node names provided in the spreadsheet have some duplicates | Build | Innovise/Mobilink | Mihai | High | Open | Medium |  |  |  |  | 19 Sep - A new CR required to update ML_Enrichment policy to lookup VAS enrichment information based on Node (IP address) as well, beside NodeAlias (for cases when no entry is available for NodeAlias but it is for Node).
032 |  | Issue | Object Server | 2011-09-19 | David P |  | Issue | Build up of un-deleted clear events in Object server. | Build | Innovise | Alex | Medium | Open | Medium |  |  |  |  | 19 Sep - Alex made a change for this related to eventId NET_VAS_IMP_001 on Friday, under observation 21 Sep - DP confirmed that this is overall improved.
033 |  | Issue | Impact | 2011-09-19 | Julian |  | Issue | One of the two Impact serversin the cluster, presently not operational | Operations | Innovise | Julian | Medium | Open | Medium |  |  |  |  | 19 Sep - We are aware of this, presentl Impact is runnoing fine no degradation, or issues. Will restore this service as soon as we are done with the closure of the remaining work on the IP policies

## CHANGE LOG
Chg # | Phase | Category | Description | Date Raised | Raised By | Approved/Denied | Date Approved | Approved by | Owner | RFC Cost £s | RFC Man Hours | RFC Impact Summary | PROGRESS - COMMENT | Status | PO Number
CR001 | 1 | Software | Add NSN manager into list of generic clear trigger | 2011-05-25 | Mihai Strava |  |  | Aamer Hussain |  |  | 1 |  | Done
CR002 | 2 | Software | Add MTTrapd-STP manager into list of generic clear trigger | 2011-06-07 | Mihai Strava |  |  | Aamer Hussain |  |  | 1 |  | Done
CR003 | 1 | Software | Add additional summary condition in trigger statement to exclude below Huawei alarms from raising tickets | 2011-06-07 | Mihai Strava |  |  | Aamer Hussain |  |  | 1 |  | Done
CR004 | 2 | Software | Updates in STP policies/rules | 2011-06-14 | Mihai Strava |  |  | Aamer Hussain |  |  | 16
CR005 | 2 | Software | Prevent STP HW events with summary not in lookup table from raising tickets | 2011-06-21 | Mihai Strava |  |  | Aamer Hussain |  |  | 1 |  | Done
CR006 | 2 | Software | Change Domain field for STP events from ‘CORE’ to ‘STP TEST’ | 2011-06-23 | Mihai Strava |  |  | Aamer Hussain |  |  | 1 |  | Done
CR007 | 1 | Software | Update OS trigger for minor IN alarms | 2011-06-28 | Mihai Strava |  |  | Aamer Hussain |  |  | 1 |  | Done
CR008 | 1 | Software | Prevent CRIT_HW_001 events generated by Nodes set into maintenance to be ticketed | 2011-06-29 | Mihai Strava |  |  | Aamer Hussain |  |  | 1 |  | Done
CR009 | 2 | Software | Update SMSC rules to set EventId=’ NET_VAS_SMSC_NIGHT_001’ | 2011-07-05 | Mihai Strava |  |  | Sohaib Ahmed |  |  | 1 |  | Done
CR010 | 2 | Software | Update table in STP lookup file | 2011-07-06 | Mihai Strava |  |  | Sohaib Ahmed |  |  | 1 |  | Done
CR011 | 1 | Software | Update OS trigger to allow all minor IN alarms to raise TTs | 2011-07-07 | Mihai Strava |  |  | Aamer Hussain |  |  | 1 |  | Done
CR012 | 2 | Software | Update STP rules by adding processing for “Alarm cleared during resync” generic resolution alarm | 2011-07-12 | Mihai Strava |  |  | Aamer Hussain |  |  | 1 |  | Done
CR013 | 1 | Software | Addition of alarms into CellDown |  | Nitesh Patel |  |  | Aamer/Azam |  |  | 6 |  | Done
CR014 | 1 | Software | Webtop tools need to be customized to log user activity such as when user clear the event, delete any event etc. |  | Nitesh Patel/Matt McCann |  |  | Aamer |  |  | 48 |  | Status TBC
CR015 | 1 | Software | Nodename lookup from IMPACT_CIINFO should be case-insensitve |  | Nitesh Patel |  |  | Aamer |  |  | 4 |  | Done
CR016 | 1 | Software | Case insensitivity during SUMMARY_LOOKUP into ML_BSSEnvironmental policy. |  | Nitesh Patel |  |  | David Pridmore |  |  | 4 |  | Done
CR017 | 1 | Software | Mobilink need the LONG_Description field to DESCRIPTION_LONGDESCRIPTION into ad-hoc report (i.e. BSS_INCIDENTS) |  | Nitesh Patel |  |  | Sehrish |  |  | 16 |  | Done
CR018 | 1 | Software | Modified AddGenericJournal to check for timestamp of ClearTime & LastOccurrence of respective events before update values into @JournalText |  | Nitesh Patel |  |  | Sehrish |  |  | 24 |  | Done
CR019 | 1 | Software | Check for status of SE after hibernation of 1st network event. Also, SE should be created with FirstOccurrence/LastOccurrence of network event. |  | Nitesh Patel |  |  | Sohaib |  |  | 12 |  | Done
CR020 | 1 | Software | BSC_Name should be populated for synthetic event (Site down or Partial site down) event created by ML_Cell_Down policy |  | Nitesh Patel |  |  | Sohaib |  |  | 4 |  | Done
CR021 | 2 | Software | Amend the “ML_CoreHardwareAlarm” policy to process the VAS environmental alarms (i.e. NET_VAS_ENV_001) same like the NET_CORE_ENV_001 alarms |  | Nitesh Patel |  |  | Iram |  |  | 32 |  | To Do
CR022 | 1 | Software | Netcool/OMNIbus core and probe for Alcatel-Lucent OMCR 1353 installation. No rules file work included |  | Alex Silva |  |  | Aamer |  |  | 8 |  | Done
CR023 | 2 | Software | Huawei M2000 probe new instance configuration for Wimax. No rules file work included. |  | Alex Silva |  |  | Aamer |  |  | 4 |  | Done
CR024 | 2 | Software | Uninstall Netcool/OMNIbus core and alcatel probe from EMS server |  | Alex Silva |  |  | Aamer |  |  | 2 |  | Done
CR025 | 2 | Software | Install Netcool/OMNIbus core and alcatel probe in mnmsun1 server |  | Alex Silva |  |  | Aamer |  |  | 8 |  | Done
CR026 | 1 | Software | Additional alarms for partial site down and RSL Link Disconnected policies |  | Alex Silva |  |  | Aamer |  |  | 8 |  | Done
CR027 | 1 | Software | Change the Manager in all Motorola rules file in order to have unique Manager for each |  | Alex Silva |  |  | Aamer |  |  | 3 |  | Done
CR028 | 2 | Software | Update IP CORE policy to check for both possibilities for A node and Z node (A node:Z node or Z node:A node) in SE and if either is found then new coming network event will be flagged as potential child. | 2011-09-14 | Mihai Strava |  |  | Sohaib |  |  | 2 |  | Done
CR029 | 2 | Software | Update ML_RaiseTT_FirstOccurrence trigger to bring SYN_IP_BLK_001 (ML_IP_Bulk_Alarm policy synthetic events) into scope. This will cause TSRM incident records to be generated for these events after the period defined by the TTHibernate Trigger | 2011-09-14 | Chris Janes |  |  | Sohaib |  |  | 2 |  | Done
CR030 | 2 | Software | Add M2000 CORE3 manager into list of generic clear trigger | 2011-09-16 | Mihai Strava |  |  | Aamer |  |  | 1
CR031 | 2 | Software | Update IP domain policies to check ITNM connectivity data for remote interface data in precedence to the ifAlias value from the network device. If match found in ITNM, populate into RemoteInterface field. If no match, use ifAlias value from network device (in remoteInterface field) to attempt to find remote node information. If no remote node identified, flag remote interface as ‘NONE’. Update IP-BSS policy and create connectivity view - Update IP-TXN policy - Update IP-CORE policy | 2011-09-16 | Julian Luxton |  |  | Sohaib |  |  | 24
CR032 | 2 | Software | Update ML_Enrichment policy to lookup VAS enrichment information based on Node (IP address) as well, beside NodeAlias (for cases when no entry is available for NodeAlias but it is for Node). | 2011-09-19 | Mihai Strava |  |  | Sohaib |  |  | 1 |  | Done
CR033 | 2 | Software | ML_RaiseTT_First Occurrence Trigger to Update day/night ticketing logic for NET_VAS_IMP_001 alarms to cover all night interval. | 2011-09-19 | Mihai Strava |  |  | Adnan |  |  | 1
CR034 | 2 | Software | Add M2000 CORE3 manager into list of generic clear trigger, as An exception case has to be added for CORBA CORE3 events to clear when occurrence time = clearance time | 2011-09-16 | Mihai Strava |  |  | Iram |  |  | 1 |  | Done

## Sheet1
open
closed