## WP1 Ericsson
WP Number & Description | Sign Off Critirea | WP Status A- Active, O - On Hold | Update Date | Update Commentary | Any Actions/Next Steps | Other related details | Target Delivery Date
WP1 - Deployment & Integration of the Ericsson Probe SME: Chris Janes Target Delivery: 31/01/12 Forecast Delivery: 12/03/12 | Deployed Integrated Probe with affected policies working | A | 2011-11-15 | Ercisson need to deploy NBI before work on this can proceed, in earnest. Their engineers are working on this. | Saad Saeed to set up a call between Chris and the Ericsson SME | Call expected Wed 16th Nov
|  |  | 2011-11-16 | Innovise to supply template LLD's for Impact policies that may be required for this work | Chris Janes to send | Chris to follow up with Saad on Friday 18th - sent 16th Nov | 2011-11-16
|  |  | 2011-11-22 | ML contacted as to progress - no response | Call with Saad 24th Nov |  | 2011-11-24
|  | O | 2011-11-22 | Likely delay of another 4wks as new tech pack required to be developed by Ericsson. LLDs for the similar IN domain policies were sent to ML for comment. Chris will follow up but this may also need to be held up till Ericsson are done with EMS related work required. | Follow up with Aamer for updates at the bi-weekly check point review calls.
|  |  | 2011-11-29 | Software not yet installed. Back end processes progressing well. Likely to be in place by the 26th Dec | Follow up with Aamer for updates at the bi-weekly check point review calls.

## WP4 Motorla GSR10
WP Number & Description | Sign Off Critirea | WP Status A- Active, O - On Hold | Update Date | Update Commentary | Any Actions/Next Steps | Other related details
WP4 -Motorolla GSR 10 Upgrade SME: Kristina Newport Target Delivery Date: 08/12/11 Forecast Delivery Date: 31/01/12 | Deployed Integrated Probe with affected policies working | O | 2011-11-15 | This probe is is not yet avavilable within the ML network. Further dates announcements re its introduction in the ML business/technology environment ar eexpected from the Planning Engineering team. | Sohaib to provide business updates. | None
|  |  | 2011-11-22 | Likely in Jan 2012 - Aamer | Follow up with ML at regualr bi-weekly calls to see if there are any changes to proposed timeline
|  |  | 2011-11-29 | Motorla not likely to happen as Motrolla activity decreasing in general. May be taken out of scope.

## WP5 Huawei M2000
WP Number & Description | Sign Off Critirea | WP Status A- Active, O - On Hold | Update Date | Update Commentary | Any Actions/Next Steps | Detailed Activity State
WP5 - Huawei M2000 Probe deployment & integration SME: Andrew Blakey/Alex Silva Target Delivery Date: 21/12/11 Forecast Delivery Date: 18/11/11 | Deployed Integrated Probe with affected policies working | A | 2011-11-15 | Iram the ML SME has been on a training course, she returns Wed 16th at which point this task can be formally initiated | Alex to set up an initial meeting with Iram. | Andy Blakey is assigned to this task. The work will be overseen by Alex Silva
|  | Closed | 2011-11-18 | ML (Sohaib Ahmed) confirmed acceptance and delivery of this Work Packet based on work functionality already delivered. | No further action required. Bill for this with agreement from Mobilink.

## WP6 IMPACT
WP Number & Description | Sign Off Critirea | WP Status A- Active, O - On Hold | Update Date | Update Commentary | Any Actions/Next Steps | Detailed Activity State
WP6 - IMPACT Development SME: Julian Luxton Target Delivery 02/01/12 Forecast Delivery: 18/01/12 Other SMEs: Sagar Shivnani, Rishikesh Bhide | Agreed policies in scope developed and tested | A | 2011-11-15 | Initial Call to be held Wed 16th Nov. | Aamer Hussain to ensure that required people are available for the initial call.
|  |  | 2011-11-16 | Nunber and broad scope of policies to be developed agreed. Up to 4 Existing Policies may need to be modified Up to 4 new Mid Complexity Policies may need to be developed Up to 2 new complex policies to be developed
|  |  | 2011-11-22 | Aamer shared some thoughts on likely policies to be modified/developed. Med complexity policy re CORE Media Outage Wi Max High Complexity Trans/BSS Domain policy for Microwave down New Policy for Huawei Network NBI New Policy re ITM events Wi-Max correlation between WiMax & BSS Modification of Fibrebreak | Arrange Call for Wed 23rd Nov to start capturing further related details
|  |  | 2011-11-23 | Existing policies: Julian to supply final LLD’s for Fiber break, wimax site down, TXN external customer, zero call issue policies • Existing policies: External customer – new triggering events will be added from NEC probe (same TT classification)–current probe lookup may move to external db lookup for commonality Existing policies: Zero call issue - Update to derive hibernation period number from percentage of cells affected New policies: Microwave correlation with BSS (HC)– requires new topology db lookup, to be discussed early next week • New Policies: ITM events – policy will create SE with classification disk/memory/CPU/log message. Julian to prepare draft LLD. CI’s needed for the monitored servers in TSRM New Policies - Huawei RTN Microwave Alarms – to be discussed after MIB is implemented • New Policies - Media Gateway Outage – Will create new type of SE which will supersede aggregation of some existing network events - Julian to start email thread with Iram on this policy | Actions steps as agreed on the call of the 23rd
|  |  | 2011-11-29 | JL to arrange calls between now and end of week Fri 2nd Dec. To get more clarity and definition on the ensuing policy work. Aamer to state a priority for the work to be taken.
|  |  | 2011-12-01 | Call held with Ml SMEs. Modify Cell Performance Policy SME Azam Modify Wi Max Site Down SME Talal Modify TXN Ext Cust SME Usman New Policy: Core Media Outage SME Iram | ML SMEs to send brief summary requirements/write up by COB Friday 2nd
|  |  | 2011-12-06 | 1. Summary requirements received for Core Media Outage and TXN external customer policies 2. Draft ITM policy LLD complete 3. Draft Core Media Outage LLD in progress | 1. review of draft ITM LLD 2. consideration of WMX dataload as new policy

## WP7 MIBS
WP Number & Description | Sign Off Critirea | WP Status A- Active, O - On Hold | Update Date | Update Commentary | Any Actions/Next Steps | Detailed Activity State
WP7 - Deployment & Integration of 2 CORE MIBS SME: Ken Edmunds Target Delivery: 08/12/11 Forecast Delivery: 26/12/11 | Deployment & Integartion of 2 CORE MIBS | O | 2011-11-15 | ML have identified the MIBS, they however need to get confirmation from the chosen Vendors of their ability and capacity to send the required traps. ML will chase this next week with a view to starting on one of the MIBS sometime during that week | ML to chase the vendors concerned, with a view to initiating work on one of the MIBS during the week of 14th Nov
|  |  | 2011-11-22 | One of the MIBS will be the Huawei MIBS, ML are expecting confirmation from the Vendor of their ability to send the required TRAPS by next Tuesday 29th Nov, once this is available we should be able to start work on this The 2nd MIB is to be substiuted by another instance of an already deployed Nokia/Net Act probe. The server required for this deployment should be available by 15th Dec | Check at the next review call if these dates are still on target
|  |  | 2011-11-29 | Aamer to share Trap info today re Huawei MIB. Iram chasing the server info readiness and NBI availability for the Nokia/Net Act probe.
|  |  | 2011-12-01 | MIB Info received. KE to start on Minday 5th Dec
|  |  | 2011-12-07 | Framework Rules Developed, looking to identify the required events

## WP8 Test Env
WP Number & Description | Sign Off Critirea | WP Status A- Active, O - On Hold | Update Date | Update Commentary | Any Actions/Next Steps | Detailed Activity State
WP8 - New Server deployment for test and staging SME: Julian Luxton Target Delivery Date: 30/11/11 Forecast Delivery Date: 16/12/12 | Correctly built and operating environment | A | 2011-11-15 | Kit is in. Infotech are building the servers with the required base OS and patches. The servers should be available Thursday 17th Nov | Aamer to ensure that the Kit is made available to us on the 17th of Nov.
|  |  | 2011-11-22 | Required bare metal recovery not possible. Will require alternative approach to this. Meeting with Infotech planned later today. Likely go with David's outlined migration plan. | David to provide update on outcome of the meeting.
|  |  | 2011-11-24 | Update from Infotech Mtng of 23rd Nov: Infotech will create the 8 new LPARS and install AIX up to the latest ML – They will be configured with the same hostname and IP addresses as the existing systems – AIX will be installed on the rootvg The existing server will be down/configured with different IP addresses during the period of migration so they don't interfere with the new systems We will migrate the filesystems from the existing systems over to the new LPARS on the datavg
|  |  | 2011-11-29 | Netback-up team believes that a successful BMR has been performed. DP will confirm this later today. If this is the case then we should be able to progress this activity in earnest. | DP to confirm status of BMR and liaise with JL on next steps.
|  |  | 2011-12-06 | 1. BMR process proved using itm1 server 2. detailed task list released for migration plan | 1. Infotech to release new LPAR's for Impact re-install 2. Continued backup and BMR for subsequent LPAR's

## WP9 ZTE
WP Number & Description | Sign Off Critirea | WP Status A- Active, O - On Hold | Update Date | Update Commentary | Any Actions/Next Steps | Detailed Activity State
ZTE Probe Deployment and Integration SME: Alex Silva Target Delivery Date: 16/12/11 Forecast Delivery Date: | Deployed Integrated Probe with affected policies working correctly | A | 2011-11-15 | Probe deployed. Enrichment & Environment policies updated and made available for testing | Alex to ensure that next agreed policy is updated to ensure the correct processing of ZTE events
|  |  | 2011-11-22 | Enrichment & BSS Environmental Polices done. Site Down LLD done sent to ML for review PSD, SD LLD's being developed will be sent for review by 25th Nov Some Rules File Work to be re-done as ML now observing in more detail. | Send out PSD, SD LLDs for review by the 25th Nov or earlier if ready. Start code dev on PSD/SD Chris Janes helping with the other related policies for the ZTE Probe
|  |  | 2011-11-29 | Missing events, clearance issue solved. PSD & SD & CD policies to be released later this week. Azam will confirm LLD today. Next policy will be RSL disconnect. Chris and Azam have had some info exchange. There is a problem generating the event required. Thus far it has not been seen. May require to create a synthetic event. Aamer will follow up with Vendor to see how this can best be progressed.
|  |  | 2011-12-06 | No feedback yet on the policies released thus far. The RSL Link Disconnect policy presently being internally tested. Awaiting event details from Mobilink for the Cell GPRS Failure, Cell Performance & X25 Policies. | AS to chase ML for feedback re policies released. AB to Release the RSL Link Disconnect Policy into Production CJ - To Chase ML for ZTE events details pertinent to the Cell GPRS, Cell Performance & X25 Policies

## Probe re-Synch
Probe Type | Testing Status | Production Status | Current Status | Waiting for | Last Update | Mobilink / Innovise /Vendor
Huawei M2000 | OK | M2000BSS1 | COMPLETE
|  | M2000BSS2 | COMPLETE
|  | M2000BSS3 | Reynch Now completing after restart of FaultService | Analysis of events from Mobilink | Not all events are resent from EMS. Tested 7 Dec | Huawei
|  | M2000CORE1 | COMPLETE
|  | M2000CORE2 | COMPLETE
|  | M2000CORE3 | Failed in production | Analysis from vendor | Handed over to Mobilink for liason with Huawei - 28 Nov | Huawei
|  | M2000WIMAX | COMPLETE
Alcatel Wimax 9753 | OK | WIMAX9753 | COMPLETE
Alcatel Q3 | NO EVENTS | ALCATELQ3OMC1 | Waiting probe patch | PMR and probe patch
|  | ALCATELQ3OMC2 | OID information sent to IBM | PMR 00501,020,808 with IBM | Went to L3 IBM with new OIDS - New probe from IBM - tested but failed 7 Dec | IBM
|  | ALCATELQ3OMC3 | Waiting probe patch | PMR and probe patch
|  | ALCATELQ3OMC4 | Waiting probe patch | PMR and probe patch
|  | ALCATELQ3OMC5 | Waiting probe patch | PMR and probe patch
|  | ALCATELQ3OMC6 | Waiting probe patch | PMR and probe patch
Huawei T2000 | OK | T2000DWDM | COMPLETE
|  | T2000SDH | Probe needs upgrading | PMR 00520,020,808 with IBM |  | IBM
Motorola 3GPP | NO EVENTS | MOTOROLA3GPPSOMCSYS2 | Waiting probe patch
|  | MOTOROLA3GPPSUNFIRE2 | Waiting probe patch
|  | MOTOROLA3GPPSUNFIRE3 | Debug information sent to IBM | PMR 00509,020,808 with IBM | Updates provided to IBM - 7th December | IBM
|  | MOTOROLA3GPPSUNFIRE4 | Probe Patched
Nokia Netact | OK | NETACT3GPPNETACT2 | COMPLETE
Siemens Switch Commander | NO EVENTS | SIEMENSSCSCR12 | Not all events are sent from EMS | PMR 00521 020 808. with IBM / Vendor Response | Waiting appropriate response from Siemens - chased 7 Dec | Siemens
ITM | PENDING | ITM | Script developed | AIX package problems using required perl SSH module | David Investigating usage of alternative module - 28 Nov | Innovise
NEC | PENDING | NEC | Probe restart will re-trigger | Testing using probe restart |  | Innovise
I2000 | PENDING | I2000 | Trigger supported using SNMP set | Vendor Input | Vendor has provided trigger using SNMP but no events in Omnibus - Chased 7 Dec | Mobilink / Vendor
STP | PENDING | STP | SNMP values for resynch not accessible | Demonstration of invoking resend on cmd line from vendor | Last response from vendor - 30 Nov, chased 7th Dec | Tekelec